## Project Overview
NovaTech Security Compliance GAP Analysis
Company | NovaTech Logistics, Inc.
Industry | Logistics and Supply Chain Technology
Employee Count | 220
Locations | Denver, CO and Dallas, TX
Assessment Frameworks | NIST CSF, ISO 27001, NIST SP 800-53
Primary Objective | Identify security risks, control gaps, and remediation priorities
Risk Scoring Method | Risk Score = Likelihood × Impact
Risk Levels
1-5 | Low
6-10 | Moderate
11-15 | High
16-25 | Critical

## Asset Inventory
Asset Inventory
Asset ID | Asset Name | Owner | Data Type | Criticality | Notes
A-01 | Employee Laptops and Workstations | IT | Business / Operational Data | High | Used by staff to access logistics platforms and email
A-02 | Transportation Management System (TMS) | Operations | Shipment / Operational Data | Critical | Core cloud platform for logistics coordination
A-03 | Microsoft 365 Email | IT | Email / Documents | High | Primary communication channel
A-04 | Shipment Tracking Database | Operations | Customer Shipment Data | Critical | Contains active shipment and customer records
A-05 | Cloud Document Storage | IT | Contracts / Internal Files | High | Stores vendor contracts and operational docs
A-06 | Vendor Remote Access Accounts | IT / Operations | Access Credentials | High | Used by third-party logistics partners

## Control Gaps
Control Gap Analysis
Domain | Current Control | Gap Identified | Risk Implication | Recommended Improvement
Access Control | Passwords required for user accounts | MFA not enabled for all cloud services | Higher risk of credential compromise | Implement MFA for all users and admins
Monitoring & Detection | Basic logs retained locally | No centralized security monitoring / alerting | Threats may go undetected | Deploy centralized logging and alerts
Vendor Access | Remote access provided to third parties | Vendor access not formally reviewed | Excessive or stale access may persist | Conduct quarterly vendor access reviews
Incident Response | Issues handled by IT as needed | No documented incident response plan | Slower containment and recovery | Develop formal incident response plan
Cloud Storage | Shared folders used by staff | Permissions not audited regularly | Sensitive files may be overshared | Perform quarterly permission audits
Security Awareness | Ad hoc reminders from IT | No formal training program | Increased phishing susceptibility | Launch recurring awareness training

## Risk Register
Risk Register
Risk ID | Asset / Process | Risk Description | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Existing Controls | Recommended Action | NIST 800-53 Mapping | Owner | Status
R-01 | Microsoft 365 Email | Phishing attack could compromise employee credentials | Phishing | MFA not enabled | 4 | 4 | 16 | Critical | Passwords required | Enable MFA and phishing training | IA-2, AT-2 | IT Manager | Open
R-02 | Transportation Management System (TMS) | Unauthorized access could disrupt logistics operations | Unauthorized Access | Weak privileged access controls | 3 | 5 | 15 | High | Passwords and antivirus | Apply least privilege and review admin access | AC-2, AC-6 | Operations / IT | Open
R-03 | Vendor Remote Access | Third-party accounts may retain unnecessary system access | Vendor Misuse / Account Abuse | No periodic vendor access review | 3 | 4 | 12 | High | Vendor access approved ad hoc | Quarterly vendor access review | AC-2 | IT / Vendor Mgmt | Open
R-04 | Cloud Document Storage | Sensitive operational files could be overshared | Data Exposure | Permissions not audited | 3 | 4 | 12 | High | Shared folders in use | Quarterly permission audit | AC-6 | IT | Open
R-05 | Incident Response Process | Lack of formal response plan could delay containment | Operational Delay | No documented incident response plan | 3 | 4 | 12 | High | IT responds informally | Create incident response plan and run tabletop | IR-8 | Security Lead | Open

## Remediation Plan
Remediation Plan
Action ID | Linked Risk ID | Remediation Action | Priority | Owner | Target Date | Status | Expected Outcome
RA-01 | R-01 | Implement MFA for all user accounts and administrators | High | IT Manager | TBD | Open | Reduces likelihood of credential compromise
RA-02 | R-02 | Review privileged roles and enforce least privilege | High | Operations / IT | TBD | Open | Limits unauthorized access to TMS
RA-03 | R-03 | Create quarterly vendor access review checklist | Moderate | Vendor Mgmt | TBD | Open | Removes stale third-party access
RA-04 | R-04 | Audit cloud storage permissions and restrict sharing | Moderate | IT | TBD | Open | Reduces accidental data exposure
RA-05 | R-05 | Develop incident response plan and run tabletop exercise | High | Security Lead | TBD | Open | Improves detection and response readiness

## Control Mapping
Recommended Improvements Mapped to NIST SP 800-53
Improvement | NIST 800-53 Control | Control Name | Notes
Implement MFA for cloud services | IA-2 | Identification and Authentication | Supports stronger login security
Quarterly vendor access reviews | AC-2 | Account Management | Ensures timely removal of stale access
Enforce least privilege in TMS | AC-6 | Least Privilege | Limits unnecessary permissions
Security awareness training | AT-2 | Literacy and Awareness Training | Reduces phishing susceptibility
Document incident response plan | IR-8 | Incident Response Plan | Improves response coordination
Backup and recovery validation | CP-9 | System Backup | Supports recovery and continuity